## Hoja1
Tasks | Member | E. Time | Real Time | D. Date
Version 0.1 (scroll an empty background) | Oscar | 2h | 2h 30 min | 2017-03-24
Version 0.2 (Welcome screen,First Level,Second Level,Congrats Screen,Back to Welcome Screen) add music |  | 4h 30min | 5h 15 min | 2017-03-31
-Welcome screen | Daniel | 30 min | 30 min | -
-First Level | Manel | 30 min | 30 min | -
-Second Level | Oscar | 30 min | 30 min | -
-Congrats Screen | Victor | 30 min | 30 min | -
-Back to Welcome Screen | Manel | 30 min | 30 min | -
-Create the Audio Module and add Music | Oscar | 2h | 2h 45 min | -
Version 0.3: (Move player without collisions, animate the player,have a background animation, have a particle shot with fx) |  | 2h 15 min | 2h | 2017-04-03
-Move player without collisions | Oscar | 45 min | 30 min | -
-Animate the player | Victor | 30 min | 30 min | -
-Have a background animation | Manel | 30 min | 30 min | -
-Have a particle shot with fx | Oscar | 30 min | 30 min | -
Version 0.4: |  | 3h 15 min | 3h 10 min | 2017-04-07
-Camera limits to the player | Oscar | 1h 45 min | 2h | -
-Add colliders to the player and its particles | Manel | 50 min | 40 min | -
-Player can collide with something of the enviroment | Victor | 30 min | 30 min | -
-Separate the fx audio in each sound effect | Daniel | 40 min | 40 min | -
Version 0.45: |  | 7h 50 min | 8h 40 min | 2017-04-21
-Add an enemy | Oscar | 20 min | 20 min | -
-Analyze it move pattern and add it to the game | Manel | 4h | 5h | -
-Make it shot to the player | Oscar | 3h 30 min | 3h 20 min | -
Version 0.5: |  | 22h 20 min | 29h 45 min | 2017-04-26
-Two players functionality | Oscar | 2h | 3h | -
-Add 4 types of enemies | Oscar | 8h | 10h | -
-Add 2 power ups | Daniel | 1h 15 min | 1h | -
-Add buildings and trees to the tilemap | Manel | 2h | 1h 30 min | -
-Do the spawn of the enemies | Manel | 2h | 2h | -
-Score display following the score points from the original game | Victor | 2h 45 min | 3h | -
-Add fx | Oscar | 50 min | 1h | -
-Remove memory leaks | Oscar | 3h | 4h | -
-Debug funcionality: God Mode,Collision Boxes. | Oscar | 2h | 1h 30 min | -
-Resize sprites | All | 2h 30 min | 2h 45 | -